**A. Kịch bản grooming sprint 2 tuần: maximum of time is 8h/sprint**

* Grooming: chia làm 2 buổi, mỗi buổi maximum 4h, SM gửi thông tin họp trước cho toàn Scrum team
	+ **Buổi 1**: thứ 5 tuần 1, thành phần bao gồm: Team product + Techlead, SA
		- *Input:* US cần tuân thủ DoD:
			* Có description: trong description có Solution
			* Design:
				+ Đối với US/task chỉ có BE thì không cần Design/mockup
				+ Đối với US có Design/mockup thì cần đính kèm vào US
		- *Cách thức thực hiện Grooming:*
			* Bước 1: PO present cho toàn team về US: 5 phút
			* Bước 2: Cả team thảo luận về US (về Description, solution, ảnh hưởng đến US/Epics khác): mỗi phiên 10 phút.
				+ Thảo luận cho đến khi cả team hiểu rõ và đúng về US.
				+ Nếu có thay trong Description thì note lại luôn.
				+ Thông tin nào chưa rõ thì cũng note lại vào Comment và Tag người liên quan
		- *Output:*
			* Description đã được tinh chỉnh
				+ Có đánh giá ảnh hưởng đến các US/epics khác
				+ Đã thống nhất Design/mockup nếu có
				+ Có 1 phần Acceptance Criteria (chưa cần chốt vì chưa đủ toàn bộ scrum team)
	+ **Buổi 2**: Sáng thứ 6 tuần 2, all team members (giải lao 1 lần/tiếng để họp hiệu quả hơn)
		- *Input*: Tuân thủ DoD như trên
		- *Cách thức thực hiện Grooming:*
			* Bước 1: PO present cho toàn team về US: 5 phút
			* Bước 2: Cả team thảo luận về US (về Description, solution, ảnh hưởng đến US/Epics khác): mỗi phiên 10 phút.
				+ Thảo luận cho đến khi cả team hiểu rõ và đúng về US.
				+ Nếu có thay đổi trong Description thì note lại luôn.
				+ Thông tin nào chưa rõ thì cũng note lại vào Comment và tag người liên quan
			* Estimate số point cho US:
				+ Toàn bộ team estimate bằng pocker fibonaci.
		- *Ouput:*
			* Cả team rõ ràng về User story
			* Chốt được Acceptance Criteria
			* Hoàn thành estimate số point cho User story

**—------------**

**English**

**Sprint Grooming Script for 2 Weeks: maximum of time is 8h/sprint**

* Grooming: Split into 2 sessions, each session maximum 4h, SM sends a summary of information to the whole Scrum team beforehand
* **Session 1**: Thursday of week 1, participants include: Product Team + Techlead, SA
	+ Input: US needs to follow the DoD:
		- Description: In the description, there should be a solution
		- Design:
			* For US/task with only BE, there is no need for Design/mockup
			* For US with Design/mockup, attach the design to the US
	+ Grooming Implementation Method:
		- Step 1: PO presents the US to the entire team: 5 minutes
		- Step 2: The whole team discusses the US (Description, solution, impact on other US/Epics): each discussion 10 minutes.
			* Discuss until the team fully understands the US.
			* If there are any changes in the description, note them down.
			* Any unclear information, also note it down in Comments and tag relevant people.
	+ Output:
		- Description is refined
		- Impact assessment on other US/Epics is done
		- Design/mockup is agreed upon if any
		- Acceptance Criteria is included (does not need to be finalized with the entire scrum team)
* **Session 2**: Friday morning of week 2, all team members (1-hour sessions for better efficiency)
	+ Input: Follow DoD as above
	+ Grooming Implementation Method:
		- Step 1: PO presents the US to the entire team: 5 minutes
		- Step 2: The whole team discusses the US (Description, solution, impact on other US/Epics): each discussion 10 minutes.
			* Discuss until the team fully understands the US.
			* If there are any changes in the description, note them down.
			* Any unclear information, also note it down in Comments and tag relevant people.
		- Estimate the points for the US:
			* The whole team estimates using the Fibonacci sequence.
	+ Output:
		- The whole team clearly understands the User story
		- Acceptance Criteria is finalized
		- Point estimation for User story is completed