**A. Kịch bản grooming sprint 2 tuần: maximum of time is 8h/sprint**

* Grooming: chia làm 2 buổi, mỗi buổi maximum 4h, SM gửi thông tin họp trước cho toàn Scrum team
  + **Buổi 1**: thứ 5 tuần 1, thành phần bao gồm: Team product + Techlead, SA
    - *Input:* US cần tuân thủ DoD:
      * Có description: trong description có Solution
      * Design:
        + Đối với US/task chỉ có BE thì không cần Design/mockup
        + Đối với US có Design/mockup thì cần đính kèm vào US
    - *Cách thức thực hiện Grooming:*
      * Bước 1: PO present cho toàn team về US: 5 phút
      * Bước 2: Cả team thảo luận về US (về Description, solution, ảnh hưởng đến US/Epics khác): mỗi phiên 10 phút.
        + Thảo luận cho đến khi cả team hiểu rõ và đúng về US.
        + Nếu có thay trong Description thì note lại luôn.
        + Thông tin nào chưa rõ thì cũng note lại vào Comment và Tag người liên quan
    - *Output:* 
      * Description đã được tinh chỉnh
        + Có đánh giá ảnh hưởng đến các US/epics khác
        + Đã thống nhất Design/mockup nếu có
        + Có 1 phần Acceptance Criteria (chưa cần chốt vì chưa đủ toàn bộ scrum team)
  + **Buổi 2**: Sáng thứ 6 tuần 2, all team members (giải lao 1 lần/tiếng để họp hiệu quả hơn)
    - *Input*: Tuân thủ DoD như trên
    - *Cách thức thực hiện Grooming:*
      * Bước 1: PO present cho toàn team về US: 5 phút
      * Bước 2: Cả team thảo luận về US (về Description, solution, ảnh hưởng đến US/Epics khác): mỗi phiên 10 phút.
        + Thảo luận cho đến khi cả team hiểu rõ và đúng về US.
        + Nếu có thay đổi trong Description thì note lại luôn.
        + Thông tin nào chưa rõ thì cũng note lại vào Comment và tag người liên quan
      * Estimate số point cho US:
        + Toàn bộ team estimate bằng pocker fibonaci.
    - *Ouput:*
      * Cả team rõ ràng về User story
      * Chốt được Acceptance Criteria
      * Hoàn thành estimate số point cho User story

**—------------**

**English**

**Sprint Grooming Script for 2 Weeks: maximum of time is 8h/sprint**

* Grooming: Split into 2 sessions, each session maximum 4h, SM sends a summary of information to the whole Scrum team beforehand
* **Session 1**: Thursday of week 1, participants include: Product Team + Techlead, SA
  + Input: US needs to follow the DoD:
    - Description: In the description, there should be a solution
    - Design:
      * For US/task with only BE, there is no need for Design/mockup
      * For US with Design/mockup, attach the design to the US
  + Grooming Implementation Method:
    - Step 1: PO presents the US to the entire team: 5 minutes
    - Step 2: The whole team discusses the US (Description, solution, impact on other US/Epics): each discussion 10 minutes.
      * Discuss until the team fully understands the US.
      * If there are any changes in the description, note them down.
      * Any unclear information, also note it down in Comments and tag relevant people.
  + Output:
    - Description is refined
    - Impact assessment on other US/Epics is done
    - Design/mockup is agreed upon if any
    - Acceptance Criteria is included (does not need to be finalized with the entire scrum team)
* **Session 2**: Friday morning of week 2, all team members (1-hour sessions for better efficiency)
  + Input: Follow DoD as above
  + Grooming Implementation Method:
    - Step 1: PO presents the US to the entire team: 5 minutes
    - Step 2: The whole team discusses the US (Description, solution, impact on other US/Epics): each discussion 10 minutes.
      * Discuss until the team fully understands the US.
      * If there are any changes in the description, note them down.
      * Any unclear information, also note it down in Comments and tag relevant people.
    - Estimate the points for the US:
      * The whole team estimates using the Fibonacci sequence.
  + Output:
    - The whole team clearly understands the User story
    - Acceptance Criteria is finalized
    - Point estimation for User story is completed